## Data
PROJECT | TASK | ASIGNEE | START DATE | DAYS REQUIRED | END DATE | PROGRESS | Projects |  | Resources |  | TODAY IS:
RED Project | Task RED 1 | Mike | 2023-01-20 | 2 | 2023-01-22 | 100% | RED Project |  | Mike |  | 2023-03-11 | *) Change to formula =TODAY()
RED Project | Task RED 2 | Bob | 2023-01-22 | 6 | 2023-01-28 | 100% | ORANGE Project |  | Sarah
RED Project | Task RED 3 | Whitney | 2023-01-23 | 17 | 2023-02-09 | 100% | BLUE Project |  | Bob
RED Project | Task RED 4 | Jordan | 2023-01-25 | 11 | 2023-02-05 | 100% | PINK Project |  | Jordan
ORANGE Project | Task ORANGE 1 | Mike | 2023-02-12 | 10 | 2023-02-22 | 100% | SILVER Project |  | Danny
ORANGE Project | Task ORANGE 2 | Bob | 2023-02-13 | 10 | 2023-02-23 | 100% | BROWN Project |  | Morgan
ORANGE Project | Task ORANGE 3 | Whitney | 2023-02-14 | 14 | 2023-02-28 | 100% | VIOLET Project |  | Whitney
ORANGE Project | Task ORANGE 4 | Sarah | 2023-02-15 | 3 | 2023-02-18 | 100%
ORANGE Project | Task ORANGE 5 | Jordan | 2023-02-16 | 15 | 2023-03-03 | 100%
ORANGE Project | Task ORANGE 6 | Sarah | 2023-02-19 | 5 | 2023-02-24 | 100%
ORANGE Project | Task ORANGE 7 | Danny | 2023-02-20 | 2 | 2023-02-22 | 100% | UNFINISHED TASKS | [6 empty] | OVERDUE TASKS
ORANGE Project | Task ORANGE 8 | Sarah | 2023-03-01 | 4 | 2023-03-05 | 100% | PROJECT | TASK | ASIGNEE | START DATE | DAYS REQUIRED | END DATE | PROGRESS | PROJECT | TASK | ASIGNEE | START DATE | DAYS REQUIRED | END DATE | PROGRESS
ORANGE Project | Task ORANGE 9 | Danny | 2023-03-03 | 1 | 2023-03-04 | 90% | ORANGE Project | Task ORANGE 9 | Danny | 2023-03-03 | 1 | 2023-03-04 | 90% | ORANGE Project | Task ORANGE 9 | Danny | 2023-03-03 | 1 | 2023-03-04 | 90%
ORANGE Project | Task ORANGE 10 | Morgan | 2023-03-05 | 1 | 2023-03-06 | 85% | ORANGE Project | Task ORANGE 10 | Morgan | 2023-03-05 | 1 | 2023-03-06 | 85% | ORANGE Project | Task ORANGE 10 | Morgan | 2023-03-05 | 1 | 2023-03-06 | 85%
BLUE Project | Task BLUE 1 | Danny | 2023-02-18 | 1 | 2023-02-19 | 100% | PINK Project | Task PINK 1 | Bob | 2023-02-25 | 14 | 2023-03-11 | 80% | PINK Project | Task PINK 4 | Sarah | 2023-03-05 | 2 | 2023-03-07 | 90%
BLUE Project | Task BLUE 2 | Danny | 2023-02-24 | 6 | 2023-03-02 | 100% | PINK Project | Task PINK 3 | Jordan | 2023-03-04 | 7 | 2023-03-11 | 75% | SILVER Project | Task SILVER 2 | Danny | 2023-03-05 | 2 | 2023-03-07 | 50%
BLUE Project | Task BLUE 3 | Mike | 2023-02-24 | 8 | 2023-03-04 | 100% | PINK Project | Task PINK 4 | Sarah | 2023-03-05 | 2 | 2023-03-07 | 90% | SILVER Project | Task SILVER 3 | Mike | 2023-03-05 | 4 | 2023-03-09 | 80%
PINK Project | Task PINK 1 | Bob | 2023-02-25 | 14 | 2023-03-11 | 80% | SILVER Project | Task SILVER 2 | Danny | 2023-03-05 | 2 | 2023-03-07 | 50% | VIOLET Project | Task VIOLET 1 | Morgan | 2023-03-06 | 2 | 2023-03-08 | 30%
PINK Project | Task PINK 2 | Whitney | 2023-03-01 | 6 | 2023-03-07 | 100% | SILVER Project | Task SILVER 3 | Mike | 2023-03-05 | 4 | 2023-03-09 | 80%
PINK Project | Task PINK 3 | Jordan | 2023-03-04 | 7 | 2023-03-11 | 75% | SILVER Project | Task SILVER 4 | Whitney | 2023-03-08 | 14 | 2023-03-22 | 15%
PINK Project | Task PINK 4 | Sarah | 2023-03-05 | 2 | 2023-03-07 | 90% | SILVER Project | Task SILVER 5 | Morgan | 2023-03-09 | 5 | 2023-03-14 | 60%
SILVER Project | Task SILVER 1 | Sarah | 2023-02-25 | 3 | 2023-02-28 | 100% | BROWN Project | Task BROWN 2 | Sarah | 2023-03-08 | 4 | 2023-03-12 | 35%
SILVER Project | Task SILVER 2 | Danny | 2023-03-05 | 2 | 2023-03-07 | 50% | BROWN Project | Task BROWN 3 | Jordan | 2023-03-12 | 7 | 2023-03-19 | 0%
SILVER Project | Task SILVER 3 | Mike | 2023-03-05 | 4 | 2023-03-09 | 80% | BROWN Project | Task BROWN 4 | Morgan | 2023-03-17 | 5 | 2023-03-22 | 0%
SILVER Project | Task SILVER 4 | Whitney | 2023-03-08 | 14 | 2023-03-22 | 15% | VIOLET Project | Task VIOLET 1 | Morgan | 2023-03-06 | 2 | 2023-03-08 | 30%
SILVER Project | Task SILVER 5 | Morgan | 2023-03-09 | 5 | 2023-03-14 | 60% | VIOLET Project | Task VIOLET 2 | Mike | 2023-03-09 | 3 | 2023-03-12 | 50%
BROWN Project | Task BROWN 1 | Morgan | 2023-03-03 | 1 | 2023-03-04 | 100% | VIOLET Project | Task VIOLET 3 | Bob | 2023-03-12 | 10 | 2023-03-22 | 0%
BROWN Project | Task BROWN 2 | Sarah | 2023-03-08 | 4 | 2023-03-12 | 35% | VIOLET Project | Task VIOLET 4 | Sarah | 2023-03-14 | 12 | 2023-03-26 | 0%
BROWN Project | Task BROWN 3 | Jordan | 2023-03-12 | 7 | 2023-03-19 | 0% | VIOLET Project | Task VIOLET 5 | Whitney | 2023-03-24 | 5 | 2023-03-29 | 0%
BROWN Project | Task BROWN 4 | Morgan | 2023-03-17 | 5 | 2023-03-22 | 0% | VIOLET Project | Task VIOLET 6 | Jordan | 2023-03-25 | 16 | 2023-04-10 | 0%
VIOLET Project | Task VIOLET 1 | Morgan | 2023-03-06 | 2 | 2023-03-08 | 30% | VIOLET Project | Task VIOLET 7 | Danny | 2023-03-08 | 5 | 2023-03-13 | 0%
VIOLET Project | Task VIOLET 2 | Mike | 2023-03-09 | 3 | 2023-03-12 | 50%
VIOLET Project | Task VIOLET 3 | Bob | 2023-03-12 | 10 | 2023-03-22 | 0%
VIOLET Project | Task VIOLET 4 | Sarah | 2023-03-14 | 12 | 2023-03-26 | 0%
VIOLET Project | Task VIOLET 5 | Whitney | 2023-03-24 | 5 | 2023-03-29 | 0%
VIOLET Project | Task VIOLET 6 | Jordan | 2023-03-25 | 16 | 2023-04-10 | 0%
VIOLET Project | Task VIOLET 7 | Danny | 2023-03-08 | 5 | 2023-03-13 | 0%
Formulas:
END DATE = [START DATE]+[DAYS REQUIRED]
END DATE = IFERROR(INDEX(Main[],SMALL(IF((Main[PROGRESS]<1),MATCH(ROW(Main[]),ROW(Main[])),""),ROWS(K14:[END DATE])),COLUMNS(A1:F1)),"")
START DATE = IFERROR(INDEX(Main[],SMALL(IF((Main[PROGRESS]<1),MATCH(ROW(Main[]),ROW(Main[])),""),ROWS(K14:[START DATE])),COLUMNS(A1:D1)),"")
START DATE = IFERROR(INDEX(K14:Q44,SMALL(IF((P14:P44<O2),MATCH(ROW(K14:Q44),ROW(K14:Q44)),""),ROWS(S14:[START DATE])),COLUMNS(A1:D1)),"")

## Calculations
Total projects: | 7 | [5 empty] | Total days scope: | 80
Total taskss: | 37 | [5 empty] | Not started | 7
[7 empty] | In Progress | 12
[7 empty] | Completed | 18
Projects | Tasks | Start | End | Days Required | Progress | Remaining | Projects | Tasks | Days Engaged | Progress | Remaining | Max man-days
All Projects | 37 | 2023-01-20 | 2023-04-10 | 243 | 68.65% | 31.35% | All Resources | 37 | 243 | 68.65% | 31.35% | 560
RED Project | 4 | 2023-01-20 | 2023-02-09 | 36 | 100% | 0% | Mike | 5 | 27 | 86% | 14% | 80
ORANGE Project | 10 | 2023-02-12 | 2023-03-06 | 65 | 97.5% | 2.5% | Sarah | 7 | 33 | 75% | 25% | 80
BLUE Project | 3 | 2023-02-18 | 2023-03-04 | 15 | 100% | 0% | Bob | 4 | 40 | 70% | 30% | 80
PINK Project | 4 | 2023-02-25 | 2023-03-11 | 29 | 86.25% | 13.75% | Jordan | 5 | 56 | 55% | 45% | 80
SILVER Project | 5 | 2023-02-25 | 2023-03-22 | 28 | 61% | 39% | Danny | 6 | 17 | 73.33% | 26.67% | 80
BROWN Project | 4 | 2023-03-03 | 2023-03-22 | 17 | 33.75% | 66.25% | Morgan | 5 | 14 | 55% | 45% | 80
VIOLET Project | 7 | 2023-03-06 | 2023-04-10 | 53 | 11.43% | 88.57% | Whitney | 5 | 56 | 63% | 37% | 80
#N/A | 0 | #N/A | #N/A | 0 | #DIV/0! |  | #N/A | 0 | 0 | #DIV/0!
#N/A | 0 | #N/A | #N/A | 0 | #DIV/0! |  | #N/A | 0 | 0 | #DIV/0!
#N/A | 0 | #N/A | #N/A | 0 | #DIV/0! |  | #N/A | 0 | 0 | #DIV/0!
Formulas:
Start = MIN(Main[START DATE])
Start = MIN(IF(Main[PROJECT]=[Projects],Main[START DATE]))
End = MAX(Main[END DATE])
End = MAX(IF(Main[PROJECT]=[Projects], Main[END DATE]))

## DASHBOARD
OVERDUE TASKS |  |  |  | Today: | 2023-03-11
PROJECT | TASK | ASIGNEE | END DATE | PROGRESS | OVERDUE
ORANGE Project | Task ORANGE 9 | Danny | 2023-03-04 | 90% | 7
ORANGE Project | Task ORANGE 10 | Morgan | 2023-03-06 | 85% | 5
PINK Project | Task PINK 4 | Sarah | 2023-03-07 | 90% | 4
SILVER Project | Task SILVER 2 | Danny | 2023-03-07 | 50% | 4
SILVER Project | Task SILVER 3 | Mike | 2023-03-09 | 80% | 2
VIOLET Project | Task VIOLET 1 | Morgan | 2023-03-08 | 30% | 3
7
TOTAL PROJECTS
37
TOTAL TASKS
37
COMPLETED
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
69%

## ©
© TemplateLab.com